## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | Create base speech-to-text and text-to-speech pipeline | Must Have | Python SpeechRecognition, gTTS | Team A | Completed
Sprint 2 | Sprint 2 | US002 | Integrate translation layer for multilingual content | Must Have | Hugging Face Transformers, GPT API | Team A | Completed
Sprint 3 | Sprint 3 | US003 | Enable real-time streaming and response generation | Should Have | WebSocket, Flask | Team A | Completed
Sprint 4 | Sprint 4 | US004 | Develop AI model for efficient speech translation with hybrid pipeline | Must Have | Azure / Hugging Face models | Team A | In Progress
Sprint 5 | Sprint 5 | US005 | Embed translation system into OTT simulation interface | Could Have | ReactJS Frontend, Flask Backend | Team A | Pending
Sprint 6 | Sprint 6 | US006 | Performance optimization and UI/UX improvement | Should Have | Memory optimization tools | Team A | Planned

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US004 | T401 | Design pipeline for hybrid model (Azure + HuggingFace) | 01-Nov | 03-Nov | Priya | Architecture Setup | Completed | 8 | bar: Day 1 to Day 3
US004 | T402 | Integrate Whisper (speech-to-text) with Translation Model | 03-Nov | 06-Nov | Arjun | Model Integration | In Progress | 12 | bar: Day 2 to Day 5
US004 | T403 | Optimize audio latency during real-time translation | 06-Nov | 09-Nov | Riya | Optimization | Planned | 10
US005 | T501 | Create OTT-like interface and embed speech model | 09-Nov | 12-Nov | Aryan | Frontend + Backend Linking | Planned | 15

## Daily Standup
Sprint | Day | Impediments | Action Taken
Sprint 4 | Day 1 | Hugging Face translation API too slow | Switched to hybrid model with cached responses
Sprint 4 | Day 2 | Render deployment failed due to memory overload | Decided to offload heavy tasks to API endpoint
Sprint 4 | Day 3 | Audio output delay noticed | Implemented asynchronous streaming response
Sprint 4 | Day 4 | GPU access required for testing | Used Google Colab Pro instance temporarily

## Retrospective
Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
Sprint 4 | 01-Nov | 10-Nov | Priya | Start using smaller model versions for tests | Stop direct deployment to Render | Continue following modular architecture | Migrated model to hybrid system for efficiency
Sprint 4 | 01-Nov | 10-Nov | Arjun | Start documenting all API calls clearly | Stop hardcoding model tokens | Continue testing latency improvements | Added API reference logs
Sprint 4 | 01-Nov | 10-Nov | Riya | Start analyzing user feedback from translation results | Stop skipping translation accuracy tests | Continue real-time performance monitoring | Introduced feedback-based fine-tuning system