## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
|  |  | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
|  |  | Translation output missing final few seconds of audio | Sprint 4 | Aryan Khurana | Functional | Added audio padding to ensure full translation output | 2025-11-03 | Closed | Working fine after re-test
|  |  | Render deployment fails due to high memory consumption | Sprint 4 | Aryan Khurana | Deployment | Switched to API-based processing instead of on-server translation | 2025-11-04 | Closed | Verified deployment success
|  |  | Latency spikes after 3 minutes of streaming | Sprint 4 | Aryan Khurana | Performance | Added asynchronous buffering for smoother playback | 2025-11-05 | Closed | Latency improved by 40%
|  |  | Audio-to-text model sometimes repeats words in translation | Sprint 4 | Aryan Khurana | AI Model | Adjusted Whisper parameters and normalized audio input | 2025-11-07 | Closed | Repetition issue resolved
|  |  | Translated video output desynchronizes from audio | Sprint 4 | Aryan Khurana | Functional | Synced timestamps using MoviePy’s audio offset feature | 2025-11-08 | Closed | Output now properly synced
|  |  | GPU dependency unavailable in Render environment | Sprint 4 | Aryan Khurana | Environment | Migrated heavy computation to Colab API | 2025-11-09 | Closed | Stable after environment switch
|  |  | WebSocket breaks when input audio is longer than 8 minutes | Sprint 5 | Aryan Khurana | Performance | Implemented segmented streaming | 2025-11-11 | Open | Needs testing on 10+ min audio
|  |  | Translation text shows wrong encoding for non-English languages | Sprint 5 | Aryan Khurana | Data Handling | Added UTF-8 normalization layer | 2025-11-12 | Closed | Encoding issue resolved successfully
Sl No | Submitted By | Submitted Date
1 | Priya | 02-Nov
2 | Arjun | 03-Nov
3 | Riya | 04-Nov
4 | Aryan | 06-Nov
5 | Priya | 07-Nov
6 | Riya | 09-Nov
7 | Arjun | 10-Nov
8 | Aryan | 11-Nov

## Sheet2
Logical
User Interface
Maintainability
Standards
Others